## BOM
disposition	what	quantity		comment	Status	Who will order or bring
	kit	25		received	have	Connie
	Battery – 9v	20			have	Clark
	small screwdrivers	15			have	Connie
loan	irons	10-12		25-35W / Need more next time	have	Clark (4), Justin (2), Margaret (1), Connie (2), Alan (1), Doug (1), others?
	solder	1		leaded	have	Justin
KEEP	brass sponges	1		pack of 30. brass wool + cat food cans	have	Connie
loan	suckers (for fixing)	2			have	Margaret, Clark
loan	braid (for fixing)	1			have	Alan, others
KEEP	flux (for fixing)	1		and toothpicks. Don’t need at every seat	have	Connie
KEEP	safety glasses	1		pack of 20	have	Connie. Justin will bring a few
consumable	D-lead wipes	1		wet wipe dispenser	have	Connie
	paper towels			donate	have	Margaret
consumable	alcohol (for cleanup)			donate	have	Connie
consumable	foam q-tips			handful	have	Connie
	blue tape				have	Clark
KEEP	diagonal cutters	12		2 per table + 2 extra. Source “Battery Hookup”	have	Clark
loan	pliers	5		lend or donate	have	Clark
KEEP	parts cups	20		Countycomm parts trays	have	Connie
KEEP	trash cups	5		yogurt containers	have	Clark
	PRINTOUTS			checklist and how-to tip sheet	have	Connie
	power			Power source, extension cables / Battery packs were great. Didn’t need generator	have	Clark, Darryl
	shade and wind protection			SHADE IS NEEDED	MISSING	MISSING – NEED NEXT TIME
consumable	table coverings			RAM board	have	Clark
KEEP	mats			silicone baking roll cut up	have	Connie
	tables			didn’t need, / occupied 2 picnic tables already in park	didn’t need	Doug
	chairs			didn’t need	didn’t need	Connie (2), Clark (how many?)
	fire extinguishers	1			have	Justin
	first aid			have this at events already	have	Rob

	pens, paper			have on hand	have

	One or two multimeters			Didn’t use	have	Margaret. Also ask coaches

## Schedule
Week #	start (Mon)	end
1	06-09	06-15	id kit – Connie	Done
2	06-16	06-22	Board approval – 6/18	Done – we want to charge $20 per participant. ID items for club to keep
3	06-23	06-29	(Field Day)

4	06-30	07-06	(4th of July)
5	07-07	07-13	look through kit, dry run with testers	Done – with Margaret. Approx 1hr including coaching
6	07-14	07-20	(Connie in NJ)
7	07-21	07-27	Send out publicity
8	07-28	08-03

9	08-04	08-10
10	08-11	08-17	Detailed instructions, educ. Packet
11	08-18	08-24	(USS Hornet) 8/23
12	08-25	08-31	Rehearsal
13	09-01	09-07
14	09-08	09-14	PAARA IN THE PARK 9/13