Coaches: Connie, Clark, Margaret, Doug, Ben, Sam, Alan

8:00 PitP setup starts. 8:45-9 Solder project setup starts.

9:45 coaches all arrived. At seats are: Covers on tables, mats. Irons, diagonal cutters, solder, handout packet (not kit yet), parts cups, pencils, trash cups. Needle-nose pliers (one per table). Handouts at seats. Solder, brass sponges. Irons not plugged in yet. Kits not handed out yet. Cutters, tape, goggles.

10:00 start. Participants start arriving

Sign-ins, payment – Margaret
Take seats for now.

10:15 Huddle up at one table. Introduction -- instructor intro to group. Introduce coaches.
- This is a skill-building project. We’re walking you through a commercial kit. Soldering is an essential skill for fixing things and making things.
- Show finished project, overview of what they’ll do.
- SAFETY: how to hold a soldering iron, WEAR EYE PROTECTORS. The solder contains lead, don’t eat it.
- No horseplay allowed. Horseplay = asked to leave the activity. This is a safety issue.
- Go over each tool – iron, cutters, sucker, pliers, brass sponge,… and why.
- When you clip the solder legs (excess wire) hold them so they don’t go flying. Wear goggles.
- don't eat or drink during, and wash hands afterward.

HOW TO SOLDER – 1, 2&, 3, 4. Refer to tip sheet.

Hand out kits. (hold onto batteries and screwdrivers for now)

Open your kit and check that all parts are there. Get a check from coach.

Do the first resistor together. Match color coding carefully. Stand them up. Demonstrate the solder method, have people go through the motion.

Insert components. Have coach check correctness.

Now plug in irons and start to solder. Have coach check.

Clip excess (keep glasses on for this part).

Repeat for resistors, transistors, capacitors, battery snap.

11:45 start helping any stragglers get to the finish line

Give participants BATTERY & SCREWDRIVER/ “pot tweaker”

Cleanup -- hands, your area