## BOM
what	quantity		comment	Status	Who will order or bring
kit	20		received	have	Connie
Battery – 9v	20			NEED	Connie or Clark
small screwdrivers	15			have	Connie
irons	10-12		Order some more cheap ones	have some, need more	Clark (4), Justin (2), Margaret (1), Connie (2), Alan (1), Doug (1), others?
solder	1		leaded	have	Justin
brass sponges	1		pack of 30. brass wool + cat food cans	have	Connie
suckers (for fixing)	2			have	Margaret, Clark
braid (for fixing)	1			have	?
flux (for fixing)	1		and toothpicks. Don’t need at every seat	have	Connie
safety glasses	1		pack of 20	have	Connie. Justin will bring a few
D-lead wipes	1		wet wipe dispenser	have	Connie
paper towels			donate	have	Margaret
alcohol (for cleanup)			donate	have	Connie
foam q-tips			handful	have	Connie
blue tape				have	Clark
diagonal cutters	12		2 per table + 2 extra. Source “Battery Hookup”	ORDER	Clark
pliers	5		lend or donate	NEED	Clark
parts cups	20		scrounge. Cat food cans	have	Connie
trash cups	5		yogurt containers	have	Clark

power			Power source, extension cables	have	Clark
shade and wind protection					?
table coverings			RAM board		Clark, Margaret
mats			silicone or other heatproof		Margaret, Clark
tables, chairs	5		We need 2 extra tables + chairs		Clark, Doug
fire extinguishers					Rob
first aid			ASK ROB WHAT IS ADVISED		Rob

pens, paper			have on hand	have

One or two multimeters				have	Margaret. Also ask coaches

## Schedule
Week #	start (Mon)	end
1	06-09	06-15	id kit – Connie	Done
2	06-16	06-22	Board approval – 6/18	Done – we want to charge $20 per participant. ID items for club to keep
3	06-23	06-29	(Field Day)

4	06-30	07-06	(4th of July)
5	07-07	07-13	look through kit, dry run with testers	Done – with Margaret. Approx 1hr including coaching
6	07-14	07-20	(Connie in NJ)
7	07-21	07-27	Send out publicity
8	07-28	08-03

9	08-04	08-10
10	08-11	08-17	Detailed instructions, educ. Packet
11	08-18	08-24	(USS Hornet) 8/23
12	08-25	08-31	Rehearsal
13	09-01	09-07
14	09-08	09-14	PAARA IN THE PARK 9/13