## BOM
what	quantity		comment	Status	Who will order or bring
kit	20		received	have	Connie
Battery – 9v	20			have	Clark
small screwdrivers	15			have	Connie
irons	10-12		Order some more cheap ones	have	Clark (4), Justin (2), Margaret (1), Connie (2), Alan (1), Doug (1), others?
solder	1		leaded	have	Justin
brass sponges	1		pack of 30. brass wool + cat food cans	have	Connie
suckers (for fixing)	2			have	Margaret, Clark
braid (for fixing)	1			have	Alan, others
flux (for fixing)	1		and toothpicks. Don’t need at every seat	have	Connie
safety glasses	1		pack of 20	have	Connie. Justin will bring a few
D-lead wipes	1		wet wipe dispenser	have	Connie
paper towels			donate	have	Margaret
alcohol (for cleanup)			donate	have	Connie
foam q-tips			handful	have	Connie
blue tape				have	Clark
diagonal cutters	12		2 per table + 2 extra. Source “Battery Hookup”	have	Clark
pliers	5		lend or donate	have	Clark
parts cups	20		Countycomm parts trays	have	Connie
trash cups	5		yogurt containers	have	Clark

power			Power source, extension cables	have	Clark
shade and wind protection					?
table coverings			RAM board		Clark
mats			silicone or other heatproof		Connie
tables, chairs	5		We need 2 extra tables + chairs		Clark, Doug, Connie (2)
fire extinguishers					Rob
first aid			ASK ROB WHAT IS ADVISED		Rob

pens, paper			have on hand	have

One or two multimeters				have	Margaret. Also ask coaches

## Schedule
Week #	start (Mon)	end
1	06-09	06-15	id kit – Connie	Done
2	06-16	06-22	Board approval – 6/18	Done – we want to charge $20 per participant. ID items for club to keep
3	06-23	06-29	(Field Day)

4	06-30	07-06	(4th of July)
5	07-07	07-13	look through kit, dry run with testers	Done – with Margaret. Approx 1hr including coaching
6	07-14	07-20	(Connie in NJ)
7	07-21	07-27	Send out publicity
8	07-28	08-03

9	08-04	08-10
10	08-11	08-17	Detailed instructions, educ. Packet
11	08-18	08-24	(USS Hornet) 8/23
12	08-25	08-31	Rehearsal
13	09-01	09-07
14	09-08	09-14	PAARA IN THE PARK 9/13